## Sheet1
PG-DESD_Project Timely Details

	DATE		Task	Task_Status		Member

	09-01-2024		Hardware acquisition	Done		Vedant T.
	09-01-2024		requirements elicitation	Done		ALL
			--USB core & cdc
			--Peripherals decided which are to be included to observe the behavious of the USB device(stm32)
	10-01-2024		--communication from the device to verify behaviour	Pending		Swapnil
	11-01-2024		-- Pin out and USB virtual COM configuration on STM32 board	Pending		Himanshu
	12-01-2024		-- Pin out and USB virtual COM configuration on STM32 board	Done		Himanshu
	12-01-2024		--refral study over USB virtual COM and CDC libusb	Done		ALL
	12-01-2024		USBd 0.2 configured for USB CDC libusb approach for communication	Done		Himanshu
			-- USB device (STM32) i.e. client side transmission and reviing function modified	Done		Himanshu
			-- Device ko module host programing initiated	Pending		Himanshu
			-- Host Promming device file operections (RWOC)	Pending		Ajay
			-- Host Programming specific for USB OTG	Pending		Ajay
			-- Host Program codded specifically for usb configured STM32 device	Pending		Swapnil
			-- Host Kernel Module for usb device	Done		ALL
			Testing	N/A		Swapnil & Vedant
			-- Tested successfully for client usb configured device (stm32)	N/A		ALL

			Test Case Implementation	Pending		Vedant T.
			Test case specific modification of the Kernel module	Pending		Swapnil
			Test case successfully implemented	N/A		Swapnil & Vedant

			Final project assembling and Testing	N/A		ALL
			Certain finishing touches & changes to the code for Demonstration	Done		ALL
			Final Testing prior Demonstration	Done		ALL